## Slide 1
Rute Sofia
Rute.sofia@sen-ception.com
11.04.2016
UMOBILE WP4
Status
<number>
Senception Lda | rute.sofia@sen-ception.com
Notes: <number>
<number>
<number>

## Slide 2
UMOBILE WP4
<number>
Senception Lda | rute.sofia@sen-ception.com
WP4 | PM
DUTH | 14
UCL | 12
UCAM | 14
COPELABS | 0
Tecnalia | 0
Tekever | 0
Senception | 15
GOWEX | 0
AFA | 10
TOTAL | 65
WP No | Work package title | Type of activity | Lead partic. | Person-months | Start month | End month
1 | Project Management | MGT | DUTH | 27 | M1 | M36
2 | Systems Requirement | RTD | UCAM | 47 | M1 | M30
3 | System and node architecture deployment | RTD | DUTH | 133 | M6 | M30
4 | Services Enablement | RTD | SENCEPTION | 65 | M6 | M30
5 | Overall platform integration and validation | RTD | GOWEX | 129 | M18 | M36
6 | Dissemination and Exploitation | RTD | AFA | 52 | M1 | M36
 | TOTAL |  |  | 453 |  | 
Notes: <number>
<number>
<number>
Keep all information about each founder in a single slide.
Insert a new slide for each additional founder.
For the “NAME” bullet, indicate the full name of the founder.
For the “Current Employment Status” bullet, be exhaustive and include all relevant information about the employer(s) - University / Research Center / Company -, job title, type of contract and start date. Should you have multiple employers or other relevant economic activities, these should be included. Also, mention all relevant legal obligations stemming from those contracts, including Intellectual Property and Confidentiality related ones. Should you be a student, your Title should be “Lic Candidate”, “Masters Candidate”, “PhD Candidate”, as appropriate. Should you have a fellowship, you should specify the type fellowship in the Type of Contract. Should you have no contract or fellowship, you should state “None” for the Type of Contract.
For the “Academic Background” bullet, include all relevant academic titles awarded.
For the “Professional Background” bullet, include all relevant former academic and non-academic employments.
For the “Other Relevant Information” bullet, include all relevant information that shows your capacity and drive to undertake the venture forward.

## Slide 3
The main objective of WP4 is to enhance the UMOBILE architecture in terms of QoS/QoE and enable solutions that take advantage of the unique features of the developed architecture. This WP will use the architecture developed during WP3 to provide a set of services.
UMOBILE WP4 Goals
Goal | Status (2016.04, month 14)
O4.1: To enable services which fully exploit the inherent opportunistic nature of communications. | 
O4.2: To enable the “Internet” experience as many people know it, with apps such as the Web, e-mail. Challenge: intermittent connectivity and/or adjusting to QoE. | 
O4.3: to develop mechanisms for processing of sensor data through context understanding. | 
O4.4: to provide different levels of QoS depending on the needs of each user/network ranging from less-than-best-effort to guaranteed services. | 
Notes: <number>

## Slide 4
UMOBILE WP4, Deliverables Status
Deliverable | Task | Status (02.09.2016) | Due on
D4.1 : Flowlet Congestion Control – Initial Report This document includes the initial specification of the rate-regulation scheme for flowlets that allows ISPs to have full control of the traffic within their network. | 4.1 | Released, M18 (July 2016) | Month 18: July 2016
D4.2 : Flowlet Congestion Control – Final Report This document defines the final specification of the rate-regulation scheme for flowlets that allows ISPs to have full control of the traffic within their network. | 4.1 | No draft yet | - Month 24 (Jan 2017)
D4.3 : Name-based Replication Priorities This document describes the mobile name-based replication system | 4.3 | drafted | - Month 24 (Jan 2017)
D4.4 : Set of QoS interfaces and algorithms This report describes the different level of services provided by UMOBILE platform | 4.1 | No draft yet | - Month 28 (May 2017)
D4.5 : Report on data collection and inference models This deliverable includes all processes developed throughout UMOBILE project that involve data collection, context understanding and data dissemination, depending on the requirements of each scenario as well as the defined priorities. | 4.2 |  | - month 30
Notes: <number>

## Slide 5
UMOBILE WP4 Milestones, Status
Goal | Status (2016.04, month 14) | Due on
MS7: QoS interfaces and mechanisms for data handling have been integrated within UMOBILE platform | No feedback | Month 30
MS8: Flowlet Congestion Control developed | No feedback | M30
Notes: <number>

## Slide 6
Task 4.3, UCL
Task 4.2, Senception
Task 4.1, UCAM
M1
M12
M6
D4.1, D4.3, D4.2, D4.4
D4.5
D4.3
D4.1: Flowlet congestion control , initial report (M18)
D4.2: Flowlet congestion control, final report (M30)
D4.3: Name-based replication priorities (M24)
D4.4: Set of QoS interfaces and algorithms (M28)
D4.5: Report on data collection and inference models (M30)
MS7: QoS interfaces and mechanisms for data handling (M30)
MS8: Flowlet congestion control developed (specs, M30)
Deliverables (editor, Senception)
Milestones
UMOBILE WP4 Roadmap, Deliverables, Milestones
M6
M30
M28
M24
Notes: <number>
Deliverables and Month of Delivery:
D2.1: Technical use-cases (M6)
D2.2: Socio-economic sustainability report (M6)
D2.3: ULOOP overall specification (M12)
Milestones and Main Expected Results:
MS3 - M2.1.: Socio-economic analysis (M6)
MS4 - M2.2: Overall specification (M12)
<number>

## Slide 7
WP4, Task 4.1 Providing different levels of QoS and flow control (UCAM, DUTH, UCL)
<number>
Senception Lda | rute.sofia@sen-ception.com
Notes: <number>
<number>
<number>
Keep all information about each founder in a single slide.
Insert a new slide for each additional founder.
For the “NAME” bullet, indicate the full name of the founder.
For the “Current Employment Status” bullet, be exhaustive and include all relevant information about the employer(s) - University / Research Center / Company -, job title, type of contract and start date. Should you have multiple employers or other relevant economic activities, these should be included. Also, mention all relevant legal obligations stemming from those contracts, including Intellectual Property and Confidentiality related ones. Should you be a student, your Title should be “Lic Candidate”, “Masters Candidate”, “PhD Candidate”, as appropriate. Should you have a fellowship, you should specify the type fellowship in the Type of Contract. Should you have no contract or fellowship, you should state “None” for the Type of Contract.
For the “Academic Background” bullet, include all relevant academic titles awarded.
For the “Professional Background” bullet, include all relevant former academic and non-academic employments.
For the “Other Relevant Information” bullet, include all relevant information that shows your capacity and drive to undertake the venture forward.

## Slide 8
T4.1 – Providing different levels of QoS and flow control
M6 –M28 (Jul 2015 – May 2017)
Leader: UCAM
Involved partners: UCAM, DUTH, UCL
Focus:
Focused on heterogeneity of the architecture and its end users.
  Multiple levels of QoS are demanded by users in possession of different devices (for ex. desktop and low cost mobile IoT devices) and accessing the application from different locations.
Intention is to provide services that range from less-than-best-effort to guaranteed QoS.
Solution: implementation of QoS mechanisms that support different levels of QoS as demanded by end users.
Scientific guidelines: QoS mechanisms will be implemented at two levels: network (flowlet-based) by UCL and application levels (service migration-based) by UCAM.
UMOBILE Task4.1 Focus
Notes: <number>

## Slide 9
Focus and Work developed so far:
UCAM has implemented a preliminary implementation of service migration over NDN where a service is migrated on the basis of usage context (e.g., server’s memory usage above the threshold) that impact the end user’s QoS.
UCL has designed a flowlet congestion control--- derived from the HotNet14 paper.
DTN supporting flowlet and Service placement for improving QoS - ?
UCAM has developed service placement algorithms aimed at meeting QoS requirements. We have evaluated them through a community network cloud.
Publications:
A. Sathiaseelan, L. Wang, A. Aucinas, G. Tyson and J. Crowcroft: SCANDEX: Service Centric Networking for Challenged Decentralised Networks, Proceedings of the ACM Mobisys Workshop on Do-it- yourself Networking: An Interdisciplinary Approach, 2015.
Wang, Liang, et al. "Pro-Diluvian: Understanding Scoped-Flooding for Content Discovery in Information-Centric Networking." Proceedings of the 2nd International Conference on Information-Centric Networking. ACM, 2015
M. Selimi, L. Cerdà-Alabern, A. Sathiaseelan, L. Veiga, F. Freitag, “Bandwidth-aware Service Placement in Community Network Clouds” IEEE LCN, 2016.
Software (with deadlines until end of the task)
UCAM will enhance its preliminary implementation of service migration over NDN by (project review date in Brussels).
The final version will be evaluated (by xx 2017) by a combination of actual tests and simulation with ndnSIM.
UCL will implement … and evaluate their network level QoS (by xx 2017) by means of …
UMOBILE Task 4.1: Current Status
Notes: <number>

## Slide 10
QoS at application level
  The effectiveness of application level QoS mechanisms depend on i) the the accuracy of the monitoring of the conditions, ii) the effectiveness of the decision engine that assesses conditions and triggers service migration.
  UCAM can currently demonstrate a preliminary implementation of service migration over NDN that migrates services when the memory of a server is dangerously reaching a threshold. The aim is only to prove that the service can be migrated.
  More realistic monitoring techniques and decision engines need to be studied, deployed and integrated.
    An example of a sophisticated monitoring algorithm is “Bandwidth-aware Service Placement in Community Network Clouds” IEEE LCN, 2016 that we have implemented.
QoS at network level
  Flowlet control, architecture integration: what is the status and who will test this later?
  demos for the review, what will this task show?
Integration of QoS at application and network level
  It seems that these mechanisms complement (and possibly disturb) each other. How they interact is an open question to UCAM and UCL.
UMOBILE Task 4.1: Open Questions and Next Steps
Notes: <number>

## Slide 11
WP4, Task 4.2 Data collection and contextual inference (SENCEPTION, AFA, DUTH)
<number>
Senception Lda | rute.sofia@sen-ception.com
Notes: <number>
<number>
<number>
Keep all information about each founder in a single slide.
Insert a new slide for each additional founder.
For the “NAME” bullet, indicate the full name of the founder.
For the “Current Employment Status” bullet, be exhaustive and include all relevant information about the employer(s) - University / Research Center / Company -, job title, type of contract and start date. Should you have multiple employers or other relevant economic activities, these should be included. Also, mention all relevant legal obligations stemming from those contracts, including Intellectual Property and Confidentiality related ones. Should you be a student, your Title should be “Lic Candidate”, “Masters Candidate”, “PhD Candidate”, as appropriate. Should you have a fellowship, you should specify the type fellowship in the Type of Contract. Should you have no contract or fellowship, you should state “None” for the Type of Contract.
For the “Academic Background” bullet, include all relevant academic titles awarded.
For the “Professional Background” bullet, include all relevant former academic and non-academic employments.
For the “Other Relevant Information” bullet, include all relevant information that shows your capacity and drive to undertake the venture forward.

## Slide 12
T4.2 – Data collection and contextual inference
M6-M30 (July 2015 – July 2017)
Leader: Senception
Involved partners: Senception, AFA, DUTH
Focus:
Focused on data capture and data processing in an efficient way, based on opportunistic and challenged environments.
Filters data based on context
Processes/propagates data based on similarities.
Key aspect 1: notion of usage contextualization and service personalization
Key aspect 2: capability to infer specific data usage context to assist in data prefetching.
Contextual inference: follows a filtering model approach to interpret data; specific utility functions (QoE) that take into account proximity and eventually location. Examples of specific contexts: roaming; entertainment; well-being.
UMOBILE WP4 Tasks & Leaders – Task4.2
Notes: <number>

## Slide 13
Focus and Work developed so far:
Studies concerning roaming context (see papers)
Application (PerSense Light) that partners can use to collect data
Proposal for the integration of a new module: sociability forecasting
Publications:
Rute C. Sofia and Paulo Mendes, A Characterization Study of Human Wireless Footprints based on non-intrusive Pervasive Sensing (2015), to APPEAR (2016)
A. Lertsinsrubtavee, L. Wang, A. Sathiaseelan, N. Weshsuwannarugs, A. Tunpan, K. Kanchanasut, J. Crowcroft , “Understanding Internet Usage and Network Locality in a Rural Community Wireless Mesh Network”, Proceeding of the 11th Asian Internet Enginee
Software (with deadlines until end of the task)
Phase I – 2016 UMOBILE demo I (April 2016)
  Framework derived from smart data capture, characterization of social routines based on Wi-Fi footprinting
  Data is kept local (SQLite) OR it can be sent to a specific server
Phase II – 2016 UMOBILE demo (December 2016) – v2.0
  Sociability forecasting software (Android)
  User recommendations and prediction of conditions for social interaction to occur derived from shared interests, affinities, and wishes via the application of social indicators to forecast sociability in space and time
  Usage context adapted to the UMOBILE architecture
  For smartphones and desktop (UNIX)
  First tests for integration as module into the UMOBILE architecture
UMOBILE Task 4.2: Current Status
Notes: <number>

## Slide 14
Open Questions:
None
Next Steps:
Discuss with partners extensions of PerSense Light, more meaningful to UMOBILE
Develop a pilot with partners as well as with external elements
  Broader characterization of roaming habits
Place traces in CRAWDAD as well as in UMOBILE?
UMOBILE Task 4.2: Open Questions and Next Steps
Notes: <number>

## Slide 15
WP4, Task 4.3 Name-Based Replication Priorities (UCL, SENCEPTION)
<number>
Senception Lda | rute.sofia@sen-ception.com
Notes: <number>
<number>
<number>
Keep all information about each founder in a single slide.
Insert a new slide for each additional founder.
For the “NAME” bullet, indicate the full name of the founder.
For the “Current Employment Status” bullet, be exhaustive and include all relevant information about the employer(s) - University / Research Center / Company -, job title, type of contract and start date. Should you have multiple employers or other relevant economic activities, these should be included. Also, mention all relevant legal obligations stemming from those contracts, including Intellectual Property and Confidentiality related ones. Should you be a student, your Title should be “Lic Candidate”, “Masters Candidate”, “PhD Candidate”, as appropriate. Should you have a fellowship, you should specify the type fellowship in the Type of Contract. Should you have no contract or fellowship, you should state “None” for the Type of Contract.
For the “Academic Background” bullet, include all relevant academic titles awarded.
For the “Professional Background” bullet, include all relevant former academic and non-academic employments.
For the “Other Relevant Information” bullet, include all relevant information that shows your capacity and drive to undertake the venture forward.

## Slide 16
T4.3 – Name-based replication priorities
M6-M24 (July 2015 - January 2017)
Leader: UCL
Involved partners: UCL, Senception
Focus:
Focused on the support of mobile name-based replication
Replication expected to be optimized by prioritisation rules.
Cases with intermittent connectivity (infrastructure not always available); messages to be stored, carried and forwarded via mobile devices.
UMOBILE WP4 Tasks & Leaders – Task4.3
Notes: <number>

## Slide 17
Focus and Work developed so far:
Studies concerning name-based replication works for emergency services
Ideas how to extend previous work within the UMOBILE project
Drafted a first document to share with the partners about how to extend it using social encounters
UMOBILE Task 4.3: Current Status
Notes: <number>

## Slide 18
Publications:
…
Software (with deadlines until end of the task)
Phase I – Task deadline (January 2017)
  Framework derived from previous work on name-based replication priorities for emergency services with social encounters
Phase II – UMOBILE demo (July 2017??)
  Implementation of the NREP solution integrated into the UMOBILE architecture over smartphone solutions (i.e. Android).
  Plan and development of a demo to show the benefits of NREP in the project review.
UMOBILE Task 4.3: Current Status
Notes: <number>

## Slide 19
Open Questions:
None
Next Steps:
We are working in the development of the extension of NREP solution with social encounters enhancement.
Discuss with Senception to possibility of an implementation over Android and the tasks evolved from it.
UMOBILE Task 4.3: Open Questions and Next Steps
Notes: <number>

## Slide 20
<number>
<number>
Senception Lda | rute.sofia@sen-ception.com
Notes: <number>
<number>
<number>